## Sheet1
Development Plan
| Functional Item | Description | Reference Documents | Notes | Requirements Complete / Approved | Team Member / Design | Design Start Date | Design Status | Design Complete / Approved | Dev Start Date | Dev Status | 1st Release Date | Final Release / Code Review | Est. Hours | Cur. Hours
Login and Registration
| User Login |  | Use Case XXX Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
User eXperience
| (Self-care) / Change Password | Overall design as to how developers will design self-care modules | Use Case XXX | Change Password Only for Release 2 |  |  |  | No Started | [5 empty] | 0 | 0
| Set Language |  | Use Case XXX | Set language to english, german, french and spanish |  |  |  | Not Started | [5 empty] | 0 | 0
User Interface Implementation
| UX Design | Layout, wireframes, prototype for portal including Theme Designs for various Themes. | Style Guide |  |  |  |  | Not Started | [5 empty] | 0 | 0
| Global Pages | what global pages will be used and where will they be stored. | User Interface Design Document | Now includes error pages and public pages. |  |  |  | Not Started | [5 empty] | 0 | 0
| JavaScript | global javascript library and it's implementation | Design Document | Rollovers, Popup windows. |  |  | 2002-09-25 | Started | [5 empty] | 0 | 0
Portal Administration
| Portal Administration | Standard portal administration functions such as creating page groups, pages, portlets, etc. | [5 empty] | Not Started |  |  | Document only for this release. |  |  | 0 | 0
| TAM Integration | Standard TAM Administration functions. | [5 empty] | Not Started |  |  | Document only for this release. |  |  | 0 | 0
| ACL's | Design Access Control Lists for the portal. | [5 empty] | Not Started |  |  | Document only for this release. |  |  | 0 | 0
Portal Services
| Common Services | Provide common functions for portlets. Form input parsing and validation, etc.. | Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
| TAM/LDAP Service | Provides reusable functionality for Change password and Login. Later can be used in R3 for User Management | Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
Password Management Portlet
| Change Password Portlet | General portlet which will be used to modify the users password | Use Case XXX Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
[14 empty] | 0 | 0
Content Management Portlet(s)
| Display Content List | Portlet that can display information from the content repository. Uses Personalization | Use Case XXX Design Document |  |  |  |  | Started | [5 empty] | 0 | 0
| Display Static Content/Page | Portlet Displays a specific piece of content to the user. | Use Case XXX Design Document |  |  |  | 2002-09-12 | Started | [5 empty] | 0 | 0
Search
| Configure Indexing | Configure the Search product to index the correct material | [5 empty] | Not Started | [5 empty] | 0 | 0
| Create Search Functionality | Search for content within the content repository | Use Case XXX Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
| Create Display/Navigation | Build the JSP pages that display search results and allow navigation. | Use Case XXX Design Document |  |  |  |  | Not Started | [5 empty] | 0 | 0
Collaboration
[14 empty] | 0 | 0
Site Analyzer
| Configure Reports | Design and create reports for Site analyzer. | May involve only documenting how reports are created specific to the CIS project. |  |  |  |  | Not Started | [5 empty] | 0 | 0
Documentation
| Development Standards | Coding Standards, Build Procedures, Version Control Issues. |  |  |  |  | 2002-09-01 | Finished | 2002-10-16 |  |  |  |  | 0 | 0
| Test Plans | Unit Test. |  | Unit Tests plans are included in Design documents for each element. |  |  |  | Not Started | [5 empty] | 0 | 0
| Database Model | Logical and Physical Database structure for use by the portal | [5 empty] | Not Started | [5 empty] | 0 | 0
| Directory Structure | [6 empty] | Not Started | [5 empty] | 0 | 0
| LDAP Schema | [6 empty] | Started | [5 empty] | 0 | 0
| Deployment Guide |  |  | The design document for each item will have individual deployment guidelines. This document will be an over all guide for the application. |  |  |  | Not Started | [5 empty] | 0 | 0
[13 empty] | Total Hours | 0 | 0
Status Codes
Not Started
Not in Plan
Started
In Progress
Near Complete
First Release
Final Release
In Test
Rework